## TEMPLATE
Cyphr Cost Estimate
| Project | Rate | Days | Fees | Charge Out @50% | Actual Rate | Actual Days | Actual Fees | Variance | Profit | Contingency | 10%
| Discovery Phase | [9 empty] | Margin Rate | 50%
| Strategy Lead (Rob) | 950 | 0.5 | 475 | 950 | [5 empty] | Total | 20570
| Strategy Lead (James) | 950 | 0.5 | 475 | 950 | [5 empty] | Planned Net | 14320
| Tech Lead (Redian) | 700 | 0 | 0 | 0 | [5 empty] | Variance | #REF!
| Producer (Verity) | 500 | 0.5 | 250 | 500 | [5 empty] | Actual Net
Overheads
[11 empty] | FX | 0.77
[11 empty] | Team | Days
|  |  | Sub Total Cost | 250
|  |  | Contingency | 10% | 240
|  |  |  | Sub Total | 2640
Design + Build Phase 1
| Strategy Lead (Rob) | 950 | 0 | 0 | 0
| Strategy Lead (James) | 950 | 1 | 950 | 1900
| Producer (Verity) | 500 | 2 | 1000 | 2000 | [5 empty] | Deliverables
| Tech Lead (Redian) | 500 | 10 | 5000 | 10000
| Developer (Mid) | 200 | 0 | 0 | 0
| QA | 450 | 1 | 450 | 900
| Support | 500 | 1 | 500 | 1000
| Hosting & 3rd Party Costs | 500 | 1 | 500 | 500
|  |  | Sub Total Cost | 6000
|  |  | Contingency | 10% | 1630
|  |  |  | Sub Total | 17930
|  |  |  | Total Cost | 6250
|  |  |  | Contingency | 1870
|  |  |  | Total | 20570
|  |  |  | Net | 14320
|  |  |  | Margin | 69.62%

## Timings + Deliverabes
Timeline
|  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6
Kick off | bar: Week 1
Interviews / Desk Research | bar: Week 1
Ideation | bar: Week 2
UX & Flows | bar: Week 3 to Week 4
UI Design | bar: Week 4
Business Model | bar: Week 2 to Week 4
Prototype (UI Clickable / PoC) | bar: Week 4 to Week 6
Deck | bar: Week 4 to Week 6
Deliverables
1. Deck / finding - Research: Understand the needs, motivations, and pain points of sports influencers and their audiences. - Define: Clearly articulate the problem you aim to solve. 2. Ideate: Brainstorm a wide range of ideas and solutions. - Creative concept - Business / Reimbursement model - UX & Flows (some) 3. Prototype / PoC: Create tangible representations for a subset of your ideas. - UI Designs - Clickable prototype / Tech PoC - Sell-in: Create internal and investment material to promote the future functionality of the service - Investor deck content (i.e. screen recording / video)

## Ratecard
Tech
Software Development (Albania) | Day Rate
- Junior Software Engineer | 130
- Mid-level Software Engineer | 200
- Senior Software Engineer | 300
- Technical Engineering leader | 380
UI/UX Designer (Albania)
- Mid-level designer | 150
- Senior designer | 200
Software Development (UK)
- Mid-weight Software Engineer | 360
Engineering Leadership: (UK)
- Technical Engineering leader | 700
UX Design
UX + UI | Day Rate
- UX Lead | 130
- Senior UX | 200
- Senior UX / UI | 300
- Mid | 380
UI/UX Designer (Albania)
- Mid-level designer | 150
- Senior designer | 200
Software Development (UK)
- Mid-weight Software Engineer | 360
Engineering Leadership: (UK)
- Technical Engineering leader | 700