## HP Crush 3.0 Gantt
HP CRUSH 3.0 — PROJECT GANTT
# | Phase | Task | Start | End | ✓ | W1: 09 Mar |  |  |  |  | W2: 16 Mar |  |  |  |  | W3: 23 Mar |  |  |  |  | W4: 30 Mar |  |  |  |  | W5: 06 Apr |  |  |  |  | W6: 13 Apr |  |  |  |  | W7: 20 Apr |  |  |  |  | W8: 27 Apr |  |  |  |  | W9: 04 May |  |  |  |  | W10: 11 May |  |  |  |  | W11: 18 May |  |  |  |  | W12: 25 May |  |  |  |  | W13: 01 Jun
[6 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
DISCOVERY & PLANNING
| Discovery & Planning | Project kickoff & stakeholder alignment | 2026-03-10 | 2026-03-10 | TRUE | bar: W1: 09 Mar M
🚩 | Discovery & Planning | Project documentation |  |  | FALSE | bar: W1: 09 Mar M
| Discovery & Planning | Requirements gathering & feature scoping - workshops | 2026-03-12 | 2026-03-18 | TRUE | bar: W1: 09 Mar T; W2: 16 Mar W
| Discovery & Planning | Technical architecture & platform decisions | 2026-04-07 | 2026-04-10 | TRUE | bar: W5: 06 Apr T to W5: 06 Apr F
🚩 | Discovery & Planning | Content taxonomy & category structure |  |  | FALSE | bar: W2: 16 Mar W to W2: 16 Mar T
| Discovery & Planning | RACI & resourcing confirmed |  | 2026-03-18 | TRUE | bar: W2: 16 Mar T
🚩 | Discovery & Planning | ✦ Feature Sign-Off |  | 2026-03-18 | TRUE | bar: W2: 16 Mar T; W3: 23 Mar T
DESIGN
| Design | Wireframes — core user journeys | 2026-03-24 | 2026-04-01 | TRUE | bar: W3: 23 Mar T to W4: 30 Mar W
| Design | UI design — general theme and style | 2026-04-01 | 2026-04-10 | TRUE | bar: W4: 30 Mar W to W5: 06 Apr F
| Design | ✦ Design Review | 2026-04-10 | 2026-04-13 | TRUE | bar: W5: 06 Apr F; W8: 27 Apr M
| Design | Design system & component library | 2026-04-10 | 2026-04-13 | TRUE | bar: W5: 06 Apr F to W6: 13 Apr M
| Design | UI design — detailed screens | 2026-04-16 | 2026-04-24 | TRUE | bar: W6: 13 Apr F to W7: 20 Apr F
| Design | ✦ Design Review | 2026-04-24 | 2026-04-27 | FALSE | bar: W7: 20 Apr F to W8: 27 Apr T
APPROVALS
15 | Approvals | Internal design review (Cyphr) | 2026-04-23 | 2026-04-27 | TRUE | bar: W7: 20 Apr F
16 | Approvals | Client design direction presentation | 2026-04-10 | 2026-04-13 | TRUE | bar: W5: 06 Apr F to W6: 13 Apr M
17 | Approvals | Feedback consolidation & revisions |  |  | FALSE
18 | Approvals | Brand & legal sign-off |  |  | FALSE
19 | Approvals | ✦ Design Approved — Dev Handoff |  |  | FALSE | bar: W8: 27 Apr T
SPRINT 1
20 | Sprint 1 | Core platform scaffolding & auth |  |  | TRUE
21 | Sprint 1 | Onboarding Flow |  |  | TRUE
22 | Sprint 1 | Admin CMS |  |  | TRUE
23 | Sprint 1 |  |  |  | FALSE
24 | Sprint 1 | Sprint 1 bug fixes & polish |  |  | FALSE
25 | Sprint 1 | ✦ Sprint 1 Feature Demo | 2026-04-30 | 2026-04-30 | FALSE | bar: W8: 27 Apr T
SPRINT 2
26 | Sprint 2 |  |  |  | FALSE
27 | Sprint 2 |  |  |  | FALSE
28 | Sprint 2 |  |  |  | FALSE
29 | Sprint 2 |  |  |  | FALSE
30 | Sprint 2 | Sprint 1 bug fixes & polish |  |  | FALSE
31 | Sprint 2 | ✦ Sprint 2 Feature Demo |  |  | FALSE
SPRINT 3
32 | Sprint 3 |  |  |  | FALSE
33 | Sprint 3 |  |  |  | FALSE
34 | Sprint 3 |  |  |  | FALSE
35 | Sprint 3 |  |  |  | FALSE
36 | Sprint 3 | Sprint 2 bug fixes & polish |  |  | FALSE
37 | Sprint 3 | ✦ Sprint 3 Feature Demo |  |  | FALSE
QA & TESTING
38 | QA & Testing | End-to-end functional testing |  |  | FALSE
39 | QA & Testing | Quiz scoring & retry logic validation |  |  | FALSE
40 | QA & Testing | Multi-platform testing (iOS/Android/Web) |  |  | FALSE
41 | QA & Testing | Performance & load testing |  |  | FALSE
42 | QA & Testing | Accessibility audit |  |  | FALSE
43 | QA & Testing | UAT with HP stakeholders |  |  | FALSE
44 | QA & Testing | ✦ App Store Submission |  |  | FALSE
LAUNCH
45 | Launch | Production environment deployment |  |  | FALSE
46 | Launch | Data migration & content population |  |  | FALSE
47 | Launch | Stakeholder sign-off & go/no-go |  |  | FALSE
48 | Launch | Soft launch & monitoring |  |  | FALSE
49 | Launch | ✦ GO LIVE |  |  | FALSE
KEY: | Discovery & Planning | Design | Approvals | Sprint 1 | Sprint 2 | W1: 09 Mar M: Sprint 3; W1: 09 Mar T: QA & Testing; W1: 09 Mar W: Launch
| ◆ = Milestone | ☐ = Mark complete by replacing with ☑

## Decision Log
Raised By | Date | Question | Response | Updates | Status
Darshan | 26th March | Invoicing – we’ll raise a PO for the full value, but ideally the invoicing would be 50% upfront and 50% on delivery. Apologies if this is already covered. |  | PO013848 | CLOSED
Darshan | 26th March | Post‑launch support – can we confirm how long support runs for once the platform has been delivered? | 3 months warranty after launch - platform CMSable so no code changes post launch within this budget |  | OPEN
Darshan | 26th March | Hosting & ongoing costs – for the initial investment, can you confirm: - How long hosting is included for? - Whether there are any ongoing costs to keep the platform live post‑delivery? | Included in project cost for hosting and waranty for 1 year - additional costs for change requests |  | CLOSED
Darshan | 26th March | Security – for HP’s security review, we’re usually asked to provide details on security standards and any penetration testing carried out. Is this something we can include? (At Samsung, for example, we had to share server and security details annually as part of an ongoing audit.) | To review what we can HP standards - Cyphr to provide Tech Spec - Verity work on policy - Verity to chase |  | OPEN
Darshan | 26th March | Exit / termination clarity – do we need to explicitly call out exit costs and risk during the build phase? For example, if HP were to pause or stop the activity before delivery, what costs would be incurred based on how far through the project we are? | Clause in SOW - work done to date is billed. First PO is done - any hours beyond 30k - keep log |  | OPEN
Verity | 23rd April | Confirmation on stock imagery/imagery used for onboarding flow expectation? |  |  | OPEN
Verity | 23rd April | Where are we hosting T&Cs - do these need to be app specific only or general HP? | Make our own for the App - overarching catch all - competition etc - make a version based on all features |  | OPEN
Verity | 23rd April | New sign ups - RDM approval flow - option to notify RDM to allow access (will stop public from being able to create accounts) or option to let in and RDMs to remove | Whitelist Currys, RDM trigger |  | OPEN
Verity | 23rd April | App store accounts - who should own? Name will display needs both Apple and Google Play | Aim is to be HP owned/branded - can we transfer later down the line? Create account and call HP UK - requires Registered business name (must match official records) Business address Legal entity type (Ltd, LLC, etc.) Company registration number D-U-N-S Number (required for Apple via Dun & Bradstreet) Website domain (often required for verification) Authority contact (someone legally allowed to sign agreements) Can HP provide this? Or we need to do BS? Blue Square company direction - BPG - speak with IT |  | OPEN
Chris | 23rd April | GDPR - not running through HP GDPR
Darshan | 23rd April | Brand approval but also data handling audit / approvals - HP procurement team | Darshan to engage with Legal team etc for any requirements, compliance - Cyphr to provide tech spec and data flow
|  | RDM workshops | Can build out within CMS and trigger through
Timeline for content and launch plan - meeting Friday, includes Video spec Style guide
Live event - 1 date or over durations?
Confirm live event / leaderboard view - Logic of live event leaderboard
Contact us email address
Push notifications can only deep link into the app
Streak cadence
HD Forma DGR Office
Admin @ HP email - for querying if not allowed account
Approvals go to RDM
Tablet view - testing, foldable devices
|  | Expired content - where does it go, how to override | Always have open unless we set an end date
Maintenance and support retainer - give £3k - Verity to detail how we'll spend, Cyphr invoice every month
Detail hosting / usage costs for post Y1